MATEX

MCP-First B2B Marketplace

Product Milestones & Roadmap

Solo Founder  |  Part-Time Build  |  March 2026 - March 2027

Prepared by: Mohamed  |  Confidential

# Table of Contents

# 1. Context & Constraints

## 1.1 Working Assumptions

| Parameter | Value | Impact |
| --- | --- | --- |
| Developer | Solo founder (Mohamed) | All development, design, DevOps by one person |
| Time Available | 15-20 hours/week (part-time, alongside RBC) | ~70 hours/month of productive dev time |
| Infrastructure Budget | $500+/month | Enables paid tiers of Supabase, Vercel, Redis, APIs |
| Primary Goal | MVP to market + grant applications in parallel | Dual-track: build & fund simultaneously |
| Technical Stack | Next.js + Supabase + MCP SDK + TypeScript | Leveraging existing Next.js/Supabase expertise |
| Target Market | Canadian scrap material traders (Ontario first) | Geographic focus reduces early complexity |
| AI Agent Advantage | Claude + MCP for accelerated development | AI-assisted coding can 3-5x solo dev speed |

## 1.2 Monthly Budget Allocation

| Service | Plan | Monthly Cost | Notes |
| --- | --- | --- | --- |
| Supabase | Pro Plan | $25 | 8GB database, 250GB storage, 50GB bandwidth |
| Vercel | Pro Plan | $20 | Serverless functions, edge network, analytics |
| Upstash Redis | Pay-as-you-go | $10-30 | Event bus, caching, auction state |
| SendGrid | Essentials (50K emails) | $20 | Transactional emails, verification |
| Twilio | Pay-as-you-go | $20-50 | SMS OTP, notifications |
| Stripe | Per transaction | 2.9% + $0.30 | No monthly fee, pay per use |
| Domain + SSL | Annual | $5 | matex.ca or similar |
| Sentry | Developer Plan | $0 | Free tier sufficient for MVP |
| Claude API | Pro + API | $50-100 | AI-assisted development + in-app features |
| Monitoring (Datadog) | Free tier | $0 | 5 hosts free, sufficient for MVP |
| DocuSign | Developer sandbox | $0 | Free for development, paid at scale |
| Total Estimated |  | $150-250/month | Well within $500 budget, room for scaling |

## 1.3 Velocity Expectations

Based on 15-20 hours/week with AI-assisted development (Claude Code, Claude in IDE), realistic velocity is approximately:

- 1 MCP server per 2 weeks (including tests, basic UI, deployment)

- 1 external bridge per 1 week (API wrapping, error handling, circuit breaker)

- UI pages: 2-3 pages per week (Next.js, responsive, basic styling)

- Total: ~2 MCP servers + UI per month as a sustainable pace

- Grant application work: 5-8 hours per application (IRAP, CDAP)

# 2. Phase Overview

The roadmap is divided into 5 phases across 12 months. Each phase has a clear deliverable and a go/no-go decision point.

| Phase | Name | Duration | MCP Servers | Deliverable |
| --- | --- | --- | --- | --- |
| Phase 0 | Foundation | Weeks 1-3 (Mar 2026) | Infrastructure only | Project scaffolding, CI/CD, Supabase schema, MCP gateway |
| Phase 1 | Core MVP | Weeks 4-11 (Apr-May 2026) | auth + listing + search + messaging + payments | Functional marketplace: list, find, message, buy |
| Phase 2 | Auctions & Trust | Weeks 12-19 (Jun-Jul 2026) | bidding + auction + escrow + inspection + booking | Live auctions, escrow protection, quality assurance |
| Phase 3 | Operations | Weeks 20-27 (Aug-Sep 2026) | logistics + contracts + tax + esign + notifications | End-to-end operations: ship, sign, track, tax |
| Phase 4 | Growth | Weeks 28-39 (Oct-Dec 2026) | dispute + pricing + analytics + admin + credit | Full platform with dispute resolution and analytics |
| Phase 5 | Scale | Weeks 40-52 (Jan-Mar 2027) | Mobile app + cross-border + optimization | Mobile, US-Canada trade, performance tuning |

Parallel Track: Grant applications (IRAP, CDAP) submitted during Phase 0-1 with existing documentation. The System Analysis and Architecture documents already completed provide strong supporting material.

# 3. Phase 0: Foundation (Weeks 1-3)

Timeline: March 16 - April 5, 2026

Effort: ~45-60 hours

Goal: Solid project foundation with infrastructure, CI/CD, and MCP gateway ready.

## 3.1 Tasks

| Week | Task | Hours | Deliverable |
| --- | --- | --- | --- |
| W1 | Initialize Next.js 14 monorepo with TypeScript | 3 | Project structure with /apps/web and /packages/mcp-servers |
| W1 | Setup Supabase project (Pro plan) with initial schema | 4 | auth_mcp + profile_mcp schemas deployed |
| W1 | Configure CI/CD: GitHub Actions + Vercel + Railway | 4 | Auto-deploy on push to main |
| W1 | Setup MCP Gateway (auth middleware + request router) | 5 | Gateway accepting authenticated MCP tool calls |
| W2 | Create MCP server template/boilerplate | 4 | Reusable template with logging, error handling, circuit breaker |
| W2 | Setup Redis (Upstash) for event bus + cache | 3 | Redis Streams consumer group pattern working |
| W2 | Implement log-mcp (append-only audit log) | 5 | Every tool call and event logged to PostgreSQL |
| W2 | Implement storage-mcp (file upload/download) | 4 | Supabase Storage wrapper with signed URLs |
| W3 | Setup Sentry error tracking + basic monitoring | 2 | Error alerts on Slack/email |
| W3 | Deploy staging environment | 3 | Full pipeline: push > test > stage > production |
| W3 | IRAP application preparation and submission | 8 | Use existing docs + business plan for IRAP |
| W3 | CDAP application preparation | 5 | Digital adoption plan submission |

## 3.2 Infrastructure Checklist

- Supabase project created (ca-central-1 region) with RLS enabled

- Vercel project linked to GitHub repo with preview deployments

- Railway project for MCP server hosting (Docker containers)

- Upstash Redis instance with eviction policy configured

- SendGrid account with domain verified for transactional emails

- Stripe account created and Connect platform configured

- GitHub repo with branch protection, PR reviews, and Actions workflows

- matex.ca domain registered and DNS configured

## 3.3 Phase 0 Exit Criteria

- MCP Gateway deployed and accepting authenticated requests

- log-mcp and storage-mcp operational and logging all tool calls

- Event bus (Redis Streams) publishing and consuming events

- CI/CD pipeline fully functional: commit to production in < 10 minutes

- IRAP application submitted

# 4. Phase 1: Core MVP (Weeks 4-11)

Timeline: April 6 - May 31, 2026

Effort: ~120-160 hours

Goal: A functional marketplace where sellers list scrap materials, buyers find and purchase them.

## 4.1 MCP Servers Built

| Server | Week | Key Tools | Priority |
| --- | --- | --- | --- |
| auth-mcp | W4-W5 | register, login, verify_email, verify_phone, enable_mfa | CRITICAL |
| profile-mcp | W5 | get_profile, update_profile, add_bank_account | HIGH |
| listing-mcp | W6-W7 | create_listing, upload_images, publish_listing, get_listing | CRITICAL |
| search-mcp | W7-W8 | search_materials, geo_search, filter_by_category, save_search | CRITICAL |
| messaging-mcp | W8-W9 | create_thread, send_message, get_thread, get_unread | HIGH |
| payments-mcp (basic) | W9-W10 | process_payment, get_wallet_balance, manage_payment_methods | CRITICAL |

## 4.2 External Bridges Built

| Bridge | Week | Purpose |
| --- | --- | --- |
| stripe-bridge | W9 | Payment processing via Stripe Connect |
| sendgrid-bridge | W4 | Email verification and transactional emails |
| twilio-bridge | W4 | SMS OTP verification |
| maps-bridge | W7 | Geocoding for listing locations and geo-search |

## 4.3 UI Pages

| Page | Week | Description |
| --- | --- | --- |
| Landing Page | W5 | Marketing homepage with value proposition, how it works, CTA |
| Registration / Login | W5 | Email + phone verification, MFA setup |
| Profile Setup | W5 | Personal info, company info, bank account linking |
| Create Listing | W6 | Multi-step form: category, details, photos, pricing, location |
| Listing Detail | W7 | Full listing view with photos, specs, map, seller info, contact button |
| Search / Browse | W8 | Search bar, filters sidebar, results grid, map view toggle |
| Messaging Inbox | W9 | Thread list, real-time chat, file sharing |
| Checkout / Payment | W10 | Order summary, payment method, Stripe checkout |
| My Dashboard (Seller) | W10-W11 | My listings, orders, messages, earnings overview |
| My Dashboard (Buyer) | W10-W11 | My purchases, saved searches, messages, spending overview |

## 4.4 Week-by-Week Plan

### Week 4: Auth + Email/SMS Bridges

- Build auth-mcp: register, login, logout, refresh_token, verify_email, verify_phone

- Build sendgrid-bridge and twilio-bridge for OTP verification

- Deploy auth_mcp schema to Supabase

- Event: auth.user.registered published and consumed by log-mcp

### Week 5: Profile + Registration UI

- Build profile-mcp: get_profile, update_profile, add_bank_account

- Build UI: Landing page, Registration flow, Login, Profile setup

- Connect Stripe Connect onboarding for sellers (express accounts)

### Week 6: Listing Creation

- Build listing-mcp: create_listing, update_listing, upload_images, publish_listing

- Deploy listing_mcp + categories schema with seed data (11 material categories)

- Build UI: Create Listing page (multi-step form with image upload)

- Full-text search index trigger deployed

### Week 7: Search + Discovery

- Build search-mcp: search_materials, geo_search, filter_by_category

- Build maps-bridge for geocoding

- Build UI: Search/Browse page with filters, results grid, map view

- Build UI: Listing Detail page

### Week 8: Messaging

- Build messaging-mcp: create_thread, send_message, get_thread, get_unread

- Supabase Realtime integration for live chat

- Build UI: Messaging inbox and chat interface

- Contact Seller button on listing detail page

### Week 9: Payments

- Build stripe-bridge: create_payment_intent, confirm_payment, create_transfer

- Build payments-mcp (basic): process_payment, manage_payment_methods

- Build UI: Checkout page with Stripe Elements

### Week 10-11: Dashboards + Polish + Testing

- Build seller and buyer dashboards

- End-to-end testing: register > list > search > message > buy

- Responsive design pass (mobile-friendly)

- Bug fixes, error handling, loading states

- SEO basics: meta tags, sitemap, structured data for listings

## 4.5 Phase 1 Exit Criteria (MVP Launch Gate)

- A seller can register, verify identity, create a listing with photos and location

- A buyer can register, search/browse materials, filter by category and location

- Buyer and seller can communicate via real-time messaging

- Buyer can purchase a listing with credit card via Stripe

- Seller receives payout to their bank account

- All actions are logged in audit trail

- Platform deployed on custom domain (matex.ca)

## 4.6 Launch Strategy

Soft Launch (End of Week 11): Invite 5-10 scrap dealers in Ontario for closed beta. Personal outreach to recyclers in GTA and Hamilton region. Free listings for first 3 months. Gather feedback aggressively.

# 5. Phase 2: Auctions & Trust (Weeks 12-19)

Timeline: June 1 - July 26, 2026

Effort: ~120-160 hours

Goal: Competitive price discovery through auctions, buyer protection through escrow, and quality assurance through inspections.

## 5.1 MCP Servers Built

| Server | Week | Key Tools | Why Now |
| --- | --- | --- | --- |
| kyc-mcp | W12-W13 | submit_documents, verify, screen_pep | Required before high-value transactions |
| escrow-mcp | W13-W14 | create_escrow, hold_funds, release, refund | Buyer/seller trust is #1 barrier |
| bidding-mcp | W14-W15 | place_bid, proxy_bid, retract, deposit | Price discovery drives marketplace value |
| auction-mcp | W15-W16 | create/start/close auction, live feed | Premium feature, higher commissions |
| inspection-mcp | W17-W18 | request, submit_report, weight_verify | Quality assurance builds trust |
| booking-mcp | W18-W19 | availability, create/confirm booking | Scheduling for inspections and visits |

## 5.2 External Bridges

| Bridge | Week | Purpose |
| --- | --- | --- |
| onfido-bridge | W12 | Identity verification (photo ID + selfie + liveness) |

## 5.3 UI Pages

| Page | Week | Description |
| --- | --- | --- |
| KYC Verification Flow | W13 | Document upload, selfie capture, status tracking |
| Auction Listing View | W15 | Bid history, countdown timer, place bid, proxy bid |
| Live Auction Room | W16 | Real-time bidding interface, live feed, chat |
| Create Auction | W16 | Schedule auction, add lots, configure rules |
| Escrow Status Page | W14 | Transaction timeline, escrow status, release/dispute |
| Inspection Request | W18 | Request inspection, choose type, schedule |
| Inspection Report View | W18 | Photos, grades, weights, pass/fail, deductions |
| Booking Calendar | W19 | Availability setup, booking management |

## 5.4 Phase 2 Exit Criteria

- Users can complete KYC verification (Level 1 and Level 2)

- Sellers can create auction listings with reserve prices

- Buyers can participate in live auctions with real-time bidding

- All transactions above $1,000 go through escrow

- Buyers can request and schedule pre-sale or delivery inspections

- Weight verification system (W1/W2/W3) operational

- At least 20 active users and 5 completed transactions

# 6. Phase 3: Operations (Weeks 20-27)

Timeline: July 27 - September 20, 2026

Effort: ~120-160 hours

Goal: End-to-end operational capabilities: shipping, contracts, tax compliance, and digital signatures.

## 6.1 MCP Servers Built

| Server | Week | Key Tools | Why Now |
| --- | --- | --- | --- |
| logistics-mcp | W20-W21 | request_quotes, book, track, confirm_delivery | Transactions need physical fulfillment |
| esign-mcp | W22-W23 | create_document, send_for_signing, status | Contracts and agreements need legal backing |
| contracts-mcp | W23-W25 | create, negotiate, activate, auto_order | Recurring buyers demand supply contracts |
| tax-mcp | W25-W26 | calculate_tax, generate_invoice, cra_export | CRA compliance is non-negotiable |
| notifications-mcp (full) | W26-W27 | send_notification, preferences, history | Replace basic email with multi-channel |

## 6.2 External Bridges

| Bridge | Week | Purpose |
| --- | --- | --- |
| carriers-bridge | W20 | Multi-carrier quoting (Day & Ross, Manitoulin, Purolator) |
| docusign-bridge | W22 | Digital signature workflows |
| fcm-bridge | W26 | Push notifications for mobile web |

## 6.3 Phase 3 Exit Criteria

- Sellers and buyers can get shipping quotes from multiple carriers and book directly

- Real-time shipment tracking operational

- Supply contracts with auto-order execution working

- eSign workflow: contract generated, signed by both parties, stored with hash

- Tax invoices auto-generated with correct GST/HST by province

- CRA-compatible tax reports exportable

- Multi-channel notifications (email + SMS + push) with user preferences

- At least 50 active users, 20+ completed transactions, 3+ supply contracts

# 7. Phase 4: Growth (Weeks 28-39)

Timeline: September 21 - December 13, 2026

Effort: ~180-240 hours

Goal: Platform maturity with dispute resolution, market intelligence, analytics, and admin tools.

## 7.1 MCP Servers Built

| Server | Week | Key Tools | Why Now |
| --- | --- | --- | --- |
| dispute-mcp | W28-W30 | file, evidence, settle, escalate, pis_score | Transaction volume requires formal disputes |
| pricing-mcp | W30-W32 | market_price, matex_index, alerts, history | Price intelligence drives platform stickiness |
| analytics-mcp | W32-W34 | dashboard, generate_report, kpis, export | Need data to grow and raise funding |
| admin-mcp | W34-W36 | manage_users, moderate, configure, audit_log | Operations require admin controls |
| credit-mcp | W36-W39 | apply, assess, activate, invoice, score | Trade credit is the killer B2B feature |

## 7.2 External Bridges

| Bridge | Week | Purpose |
| --- | --- | --- |
| lme-bridge | W30 | London Metal Exchange real-time pricing |
| fastmarkets-bridge | W31 | Scrap-specific market data |
| equifax-bridge | W37 | Business credit checks for credit facility |
| accounting-bridge | W35 | QuickBooks/Xero sync for sellers |

## 7.3 Phase 4 Exit Criteria

- Three-tier dispute resolution fully operational

- Platform Integrity Score (PIS) calculated for all users

- Live market price data displayed alongside listings

- Matex Price Index (MPI) calculated from platform transaction data

- Admin dashboard with user management, moderation, and KPI monitoring

- Trade credit facility available for qualified buyers (Basic tier minimum)

- Analytics reports: revenue, GMV, user growth, transaction volume

- Target: 200+ active users, $500K+ GMV, 100+ transactions

# 8. Phase 5: Scale (Weeks 40-52)

Timeline: December 14, 2026 - March 14, 2027

Effort: ~180-240 hours

Goal: Mobile app, cross-border US-Canada trade, performance optimization, and scaling.

## 8.1 Deliverables

| Deliverable | Weeks | Description |
| --- | --- | --- |
| React Native Mobile App (v1) | W40-W46 | Core flows: browse, bid, message, inspect (camera), notifications |
| Cross-Border Module | W46-W49 | US-Canada customs docs, HS codes, USMCA, currency conversion, OFAC screening |
| Performance Optimization | W49-W51 | Database query optimization, caching strategy, CDN configuration, load testing |
| Security Audit | W51-W52 | Third-party penetration test, vulnerability scan, compliance review |
| Series Seed Preparation | W50-W52 | Pitch deck, financial projections, investor outreach materials |

## 8.2 Phase 5 Exit Criteria

- Mobile app available on App Store and Google Play

- At least one US-Canada cross-border transaction completed

- Platform handles 100 concurrent users without performance degradation

- Security audit passed with no critical or high findings

- Target: 500+ active users, $2M+ GMV, profitable unit economics

# 9. Grant Application Strategy (Parallel Track)

Grant applications run in parallel with development and do not block any milestones. The documentation already produced (System Analysis, MCP Architecture, DB Schema) provides strong supporting material.

## 9.1 IRAP (NRC Industrial Research Assistance Program)

| Item | Details |
| --- | --- |
| What | Non-repayable contributions up to $500K for R&D projects |
| Eligibility | Canadian incorporated SME, fewer than 500 employees, for-profit |
| Apply When | Phase 0 (Week 3) - submit with existing documentation |
| Funding Covers | Developer salary/contractor costs, cloud infrastructure, third-party APIs |
| R&D Angle | MCP-first architecture as novel AI-native marketplace approach; real-time auction engine; AI-powered material grading |
| Timeline | 4-6 weeks for initial ITA meeting, 2-3 months to approval |
| Expected Amount | $50K-$150K (based on solo founder, part-time) |
| Key Documents | Business plan, System Analysis Doc, Architecture Doc, financial projections |

## 9.2 CDAP (Canada Digital Adoption Program)

| Item | Details |
| --- | --- |
| What | Boost Your Business Technology grant: up to $15,000 + $100K BDC loan at 0% |
| Eligibility | Canadian-owned business, 1+ employee, $500K-$100M revenue |
| Apply When | Phase 0 (Week 3) - submit digital adoption plan |
| Funding Covers | Digital technology adoption and transformation |
| Key Requirement | Must work with a CDAP-approved digital advisor |
| Timeline | 2-4 weeks to approval |
| Expected Amount | $15,000 grant + potential $100K interest-free BDC loan |
| Key Documents | Digital adoption plan (use System Analysis as basis) |

## 9.3 Other Funding Opportunities

| Program | Amount | Apply When | Fit |
| --- | --- | --- | --- |
| Ontario Scale-Up Vouchers | Up to $50K | Phase 2 (once MVP live) | Technology adoption for scaling SMEs |
| Startup Visa (if incorporating) | N/A | Phase 1 | Could attract international technical co-founder |
| FedDev Ontario | Up to $1M | Phase 3-4 | Requires operational business with growth plan |
| BDC Advisory / Loans | Varies | Phase 2 | Business development advisory + low-interest loans |
| Mitacs (if hiring intern) | $15K per term | Phase 3+ | Subsidized developer/research interns |

# 10. Key Metrics & Decision Points

## 10.1 North Star Metrics

| Metric | Phase 1 Target | Phase 2 | Phase 3 | Phase 4 | Phase 5 |
| --- | --- | --- | --- | --- | --- |
| Active Users | 10 | 30 | 80 | 200 | 500+ |
| Listings Active | 20 | 60 | 150 | 400 | 1,000+ |
| Transactions/Month | 3 | 10 | 30 | 80 | 200+ |
| GMV/Month | $10K | $50K | $150K | $400K | $1M+ |
| Revenue/Month (commission) | $350 | $2K | $5K | $14K | $35K+ |
| Repeat Buyer Rate | N/A | 20% | 30% | 40% | 50%+ |
| Avg Transaction Value | $3K | $5K | $5K | $5K | $5K |

## 10.2 Go / No-Go Decision Points

| Decision Point | When | Go Criteria | No-Go Action |
| --- | --- | --- | --- |
| MVP Launch Gate | End of Phase 1 (Week 11) | Core flow works end-to-end, 5+ beta testers committed | Fix critical bugs, extend by 2 weeks max |
| Product-Market Fit Check | End of Phase 2 (Week 19) | 20+ users, 5+ transactions, positive feedback | Pivot: consider different vertical or geography |
| Operations Viability | End of Phase 3 (Week 27) | 50+ users, revenue covering infrastructure costs | Reduce scope: focus on most used features only |
| Growth Investment Decision | End of Phase 4 (Week 39) | 200+ users, $500K GMV, grant funding received | Stay lean: defer Phase 5, focus on profitability |
| Scale / Raise Decision | End of Phase 5 (Week 52) | 500+ users, $2M GMV, clear unit economics | Bootstrap: continue profitable growth without raise |

# 11. Risks & Mitigations

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Solo developer burnout (part-time alongside RBC) | HIGH | CRITICAL | Strict 20h/week cap. No weekend death marches. AI-assisted coding to maintain velocity. Take 1 week off every 8 weeks. |
| Chicken-and-egg: no sellers without buyers, no buyers without sellers | HIGH | CRITICAL | Seed supply side first: personally onboard 5-10 scrap dealers with free listings. Create demand through targeted outreach to recyclers. |
| Scrap traders are not tech-savvy, low digital adoption | MEDIUM | HIGH | Ultra-simple UI. Phone support during onboarding. Visit scrap yards in person for demos. Build trust through face-to-face relationships. |
| Stripe Connect regulatory complexity for marketplace | MEDIUM | MEDIUM | Start with simple direct payments. Escrow via Stripe Connect Express accounts. Consult Stripe documentation early. |
| Grant applications rejected | MEDIUM | LOW | Grants are bonus, not dependency. Platform is buildable within personal budget. Reapply with live product data. |
| Security incident or data breach | LOW | CRITICAL | Supabase managed security. RLS on all tables. No PII in logs. Stripe handles payment data. Penetration test in Phase 5. |
| MCP protocol changes or becomes obsolete | LOW | MEDIUM | MCP servers are essentially Node.js services. If MCP changes, the business logic stays. Only the transport layer changes. |
| RBC workload increases, less time for Matex | MEDIUM | HIGH | Milestone dates are estimates, not commitments. Phases can stretch. Core architecture is done; implementation is incremental. |

# 12. Immediate Next Steps (This Week)

To turn this plan into action, here are the concrete steps for the next 7 days:

- Register matex.ca domain (if not already done)

- Create Supabase project on Pro plan (ca-central-1 region)

- Initialize GitHub repository with Next.js 14 monorepo structure

- Deploy the database schema (auth_mcp + profile_mcp schemas first)

- Setup Vercel project linked to GitHub with auto-deploy

- Create Stripe account and enable Connect platform

- Create SendGrid account and verify sending domain

- Start IRAP application: contact local NRC-IRAP office to schedule ITA meeting

- Download CDAP application form and begin digital adoption plan

- Build MCP server boilerplate template with logging and error handling

First milestone: MCP Gateway + auth-mcp + log-mcp deployed and accepting requests by end of Week 2.

## 12.1 Document Revision History

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| 1.0 | March 2026 | Mohamed | Initial milestones and roadmap document |